## Timesheet
DMIT 2511 A02 Time Sheet
Student Name: Ojas Anand
Project Name: DisOriented
Weekly Date Range Mon - Sun | Mon Hrs | Tue Hrs | Wed Hrs | Thu Hrs | Fri Hrs | Sat Hrs | Sun Hrs | Total Hrs | Description of Work | Problems or Issues
Feb 2 - Fab8 | 0 | 2 (in class) | 2 (in class) + 2 | 0 | 2 (in class)+ 1 | 0 | 0 | 9 | Created Unity Project, set up version control, Established project architecture, Imported needed packages, configured input system for mouse, keyboard and gamepad, Wrote singleton base class, and set up resource type and definition | No real issues, couldn’t work on it too much cause CAMS was very research intensive during this period. Learned how to create the manager infrastructure and singleton pattern !
Feb 9 - Fab 15 | 0 | 2 (in class) | 2 (in class) | 0 | 2 + 1 (in Class) | 0 | 0 | 7 | Set up resource events, learnt about heap allocation and structs, Wrote resource manager, created tests for the manager, Also wrote the save data script | CAMS took up most of my time this week , but I managed to get the resourcemanager made which was a big win. I hate writing test code tho, so that was an absolte struggle
Feb 16 - Fab 22 | 0 | 0 | 0 | 3 | 2 | 5 | 4 | 14 | Set up the Save Manager, much easier when building upon the general manager pattern and we covered something similar for Sujan's class, Wrote test code for it and tested, Wrote BootLoader script and then tested the whole resourcemanager + savemanager system. Also made the time system with timedefinition SO, time events and time Manager | Was crunching during reading week trying to polish my portfolio for march, pulled this up in the later half of the week. Spent a LOT of time debugging the time manager and handling edge cases
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lists
2026-01-05 to 2026-01-11
2026-01-12 to 2026-01-18
2026-01-19 to 2026-01-25
2026-01-26 to 2026-02-01
2026-02-02 to 2026-02-08
2026-02-09 to 2026-02-15
2026-02-16 to 2026-02-22
2026-02-23 to 2026-03-01
2026-03-02 to 2026-03-08
2026-03-09 to 2026-03-15
2026-03-16 to 2026-03-22
2026-03-23 to 2026-03-29
2026-03-30 to 2026-04-05
2026-04-06 to 2026-04-12
2026-04-13 to 2026-04-19
2026-04-20 to 2026-04-26
2026-04-27 to 2026-05-03
2026-05-04 to 2026-05-10
2026-05-11 to 2026-05-17
2026-05-18 to 2026-05-24
2026-05-25 to 2026-05-31
2026-06-01 to 2026-06-07
2026-06-08 to 2026-06-14
2026-06-15 to 2026-06-21
2026-06-22 to 2026-06-28
2026-06-29 to 2026-07-05
2026-07-06 to 2026-07-12
2026-07-13 to 2026-07-19
2026-07-20 to 2026-07-26
2026-07-27 to 2026-08-02
2026-08-03 to 2026-08-09
2026-08-10 to 2026-08-16
2026-08-17 to 2026-08-23
2026-08-24 to 2026-08-30
2026-08-31 to 2026-09-06
2026-09-07 to 2026-09-13
2026-09-14 to 2026-09-20
2026-09-21 to 2026-09-27
2026-09-28 to 2026-10-04
2026-10-05 to 2026-10-11
2026-10-12 to 2026-10-18
2026-10-19 to 2026-10-25
2026-10-26 to 2026-11-01
2026-11-02 to 2026-11-08
2026-11-09 to 2026-11-15
2026-11-16 to 2026-11-22
2026-11-23 to 2026-11-29
2026-11-30 to 2026-12-06
2026-12-07 to 2026-12-13
2026-12-14 to 2026-12-20
2026-12-21 to 2026-12-27
2026-12-28 to 2027-01-03